## Dashboard
Engineering Design TA — Progress Dashboard · Fall 2026
Everything here is calculated from the other tabs. Update task Status in 'Task Tracker' and order Status in 'Supplies & Orders' — this page follows.
| Today | Key date (from meeting) | Days to key date | One-time tasks done | Progress (one-time tasks) | Overdue | Due in next 7 days
2026-10-01
| Progress by category | [8 empty] | Lab prep snapshot
| Category | Tasks | Done | Remaining | In progress | Waiting | Not started | Ongoing | % Done | Supplies — must-have cost (est.)
| 1. TA Requirements | [8 empty] | Supplies — everything listed (upper bound)
| 2. Lab Safety & Access | [8 empty] | Items to check in lab / order
| 3. Supplies & Chemicals | [8 empty] | Items ordered (in transit)
| 4. DO Measurement Method | [8 empty] | Items received / in lab
| 5. Lab & Project Setup | [8 empty] | Oxygenation groups
| 6. Academic & Assessment | [8 empty] | DO saturation at the lab (mg/L)
| 7. Student Project Guidance | [8 empty] | Na₂S₂O₄ dose per 1 L (g)
| TOTAL | [8 empty] | Na₂S₂O₄ for whole class (g)
Remaining = one-time tasks not done (In progress + Waiting + Not started). Ongoing tasks are not counted in % done.
| Next deadlines (not done) | [8 empty] | Top DO measurement method (gives mg/L)
| Task ID | Task |  |  | Target | Days left | Who |  |  | Top color indicator (qualitative only)
Note on C5: October 1 was the date given in the meeting with the professor (with the < $80 per group budget, 4–5 students per group). Confirm exactly what is due and edit if needed.

## Read Me
How to use this workbook
TA Progress Tracker · Engineering Design · Fall 2026
Tabs
Dashboard | Overall progress, days to the key date, overdue tasks, next deadlines, supply cost and dose summary — all formulas.
Task Tracker | Every task from the previous TA's list + the meeting with Dr. Gomez. Change Status with the drop-down; Days Left / Flag update daily. Filter by Category, Who or Flag.
Supplies & Orders | Part A: shopping list with Sigma-Aldrich / vendor links, quantities, prices, status. Part B: Na₂S₂O₄ dose to deoxygenate 1 L of water, scaled to the class. Part C: methylene blue stock and dilution.
DO Methods | Options to measure dissolved oxygen in a closed container (the old DO probe is damaged), scored on the previous TA's criteria with editable weights.
Contacts | Who to ask for what; open tasks per person are counted automatically.
Meeting Notes | Log of meetings (the first entry is your meeting with the professor).
Color legend
Blue text, pale-yellow cell | Input — type or choose here (status, dates, quantities, prices, calculator inputs, scores, weights).
Black text | Formula — updates automatically; do not type over it.
Green result cell | Key result of a calculation (e.g., grams of Na₂S₂O₄ per 1 L).
Strike-through green row | Task marked Done.
Red / yellow flag | Overdue / due within 3 days.
Notes
Key date | October 1, 2026 comes from the meeting notes ('October 1, under $80, 4 to 5 students per group'). Confirm with Dr. Gomez what is due that day (task T13).
Prices | Checked on vendor pages on Sep 22, 2026 (hover over a price for its source). Sigma-Aldrich shows TTU prices only after logging in — type the price in the blue cell when you see it. Shipping/tax not included.
Dose calculator | Assumptions: 1:1 dithionite:O₂, 1.5× excess, 82.5% purity (Sigma 157953 assay), 22 °C water, 976 m elevation. DO saturation uses the USGS/Standard Methods equation with the exact pressure correction; a check table compares it with published values. Pilot-test before class.
DO Methods | Scores (1–5) are starting suggestions from the research — edit them and the weights; the weighted score and rank recalculate. The previous TA's note says these are initial alternatives, not a final selection.
Tasks | Rows marked 'Suggested (verify)' are my additions (pilot test, waste containers). Target dates are suggestions — edit them. Ongoing tasks are not counted in the % complete.
Related file | Student_Roster_and_Quiz1_Grades.xlsx — roster, group assignment and Quiz 1 grades.

## Task Tracker
Task Tracker — Everything I Need To Do
Change Status with the drop-down; edit Target dates (blue). Days Left and Flag update every day. Source: previous TA's responsibilities list + meeting with Dr. Gomez + suggestions (marked).
ID | Category | Task | Details / Notes | Who / Contact | Priority | Status | Target Date | Date Done | Days Left | Flag | Source | sort key (helper)
T01 | 1. TA Requirements | Complete all required laboratory safety training courses | Must be done BEFORE participating in any laboratory activity. | TTU EHS (online training) | High | In progress | 2026-09-25 |  |  |  | Previous TA list
T02 | 1. TA Requirements | Keep training current + check for extra training for specific lab facilities/equipment | Ask whether the lab or any equipment (balances, fume hood, chemical storage) needs its own training. | Mike Nichols / EHS | Medium | Ongoing | 2026-09-25 |  |  |  | Previous TA list
T03 | 1. TA Requirements | Complete FERPA training | Required to get Canvas access and to perform TA duties (grades). | TTU (FERPA course) | High | Done | 2026-09-24 |  |  |  | Previous TA list
T04 | 2. Lab Safety & Access | Verify student safety equipment with Mike Nichols (lab coats, safety glasses, gloves) | Lab coats and gloves are already available. Check quantities and condition for ~52 students. | Mike Nichols | High | Done | 2026-09-25 |  |  |  | Previous TA list
T05 | 2. Lab Safety & Access | Follow up: safety-glasses rack/support installed and glasses ready for students | Safety glasses are pending a support/rack for storage. Once installed, the equipment is ready for student use. | Mike Nichols | Medium | Done | 2026-09-30 |  |  |  | Previous TA list
T06 | 2. Lab Safety & Access | Get lab keys and access | Coordinate pick-up of keys / card access for the lab. | Mike Nichols | High | In progress | 2026-09-25 |  |  |  | Previous TA list
T07 | 3. Supplies & Chemicals | Ask Dr. Gomez for the FOP (purchasing account) to place orders | FOP = Fund-Organization-Program account used for TTU purchases. Needed before any order. | Dr. Gomez | High | In progress | 2026-09-23 |  |  |  | Meeting w/ Dr. Gomez
T08 | 3. Supplies & Chemicals | Check with lab personnel which chemicals are already available | Confirm whether sodium dithionite (Na₂S₂O₄, 'sodium hydrosulfite') and methylene blue are in stock and not expired. Update 'Supplies & Orders' → Status. | Lab personnel / stockroom | High | In progress | 2026-09-24 |  |  |  | Previous TA list
T09 | 3. Supplies & Chemicals | Order sodium dithionite (Na₂S₂O₄) if not in stock | Sigma-Aldrich — see 'Supplies & Orders' Part A. Amount needed: Part B calculator. | Dr. Gomez (FOP) | High | Not started | 2026-09-25 |  |  |  | Meeting w/ Dr. Gomez
T10 | 3. Supplies & Chemicals | Order methylene blue dye | Sigma-Aldrich — see 'Supplies & Orders'. Used for the dye-removal half (and possibly as the O₂ color indicator). | Dr. Gomez (FOP) | High | Not started | 2026-09-25 |  |  |  | Meeting w/ Dr. Gomez
T11 | 3. Supplies & Chemicals | Compare ~1 L plastic containers with lids and pick one | Must fit the experiment (clear walls to see color, tight lid) and the budget. Example vessel from the previous TA: https://a.co/d/0c6b1Ve2 | — | High | Not started | 2026-09-24 |  |  |  | Previous TA list
T12 | 3. Supplies & Chemicals | Buy the plastic containers with lids (500 mL–1 L, cheap) | Meeting said 11 (likely one per group for the whole class: 52 students ÷ 5 → 11 groups); previous TA planned 12 (11 + 1 spare). | Dr. Gomez (FOP) | High | Not started | 2026-09-25 |  |  |  | Meeting w/ Dr. Gomez
T13 | 3. Supplies & Chemicals | Clarify what is due Oct 1 and what the 'under $80' limit applies to | From the meeting: 'October 1, under $80 (4 to 5 students per group)'. Confirm with Dr. Gomez whether $80 is per group (student prototype budget) and tell the students. | Dr. Gomez | High | In progress | 2026-09-24 |  |  |  | Meeting w/ Dr. Gomez
T14 | 4. DO Measurement Method | Investigate DO measurement methods for a closed container | The traditional DO probe is damaged. Start with optical sensor spots, colorimetric methods and Winkler titration — see 'DO Methods' tab. | — | High | In progress | 2026-09-26 |  |  |  | Previous TA list
T15 | 4. DO Measurement Method | Score the alternatives and choose a method | Criteria: time (~2 min), closed system, opening/penetration of container, accuracy, ease of use, equipment availability, cost. These are starting alternatives, not a final choice. | Dr. Gomez | High | In progress | 2026-09-28 |  |  |  | Previous TA list
T16 | 4. DO Measurement Method | Test the color-indicator idea (methylene blue + Na₂S₂O₄) | From the meeting: 'some sort of buffer that changes color with O₂'. Dithionite turns methylene blue colorless; it turns blue again as O₂ diffuses back in. | — | Medium | Not started | 2026-09-29 |  |  |  | Meeting w/ Dr. Gomez
T17 | 4. DO Measurement Method | Pilot-test the full oxygen-diffusion setup before class | Deoxygenate 1 L with the dose from Part B, seal, and measure DO over time. Expect a lag while leftover dithionite is used up (Part B, row V). Adjust the excess factor if the water re-oxygenates too fast or too slowly. | — | High | Not started | 2026-09-30 |  |  |  | Suggested (verify)
T18 | 5. Lab & Project Setup | Support laboratory preparation before student activities begin | Benches, glassware, labels, balance, deionized water. | Mike Nichols | Medium | Not started | 2026-09-30 |  |  |  | Previous TA list
T19 | 5. Lab & Project Setup | Disassemble previous years' water-treatment prototypes | Remove components so students cannot simply reuse or copy earlier designs. | — | Medium | Not started | 2026-09-30 |  |  |  | Previous TA list
T20 | 5. Lab & Project Setup | Confirm the project split and form groups | Half the class: methylene blue removal; other half: oxygenation. 4–5 students per group. Use the Roster tab in the gradebook to assign groups. | Dr. Gomez | High | Not started | 2026-09-25 |  |  |  | Meeting w/ Dr. Gomez
T21 | 5. Lab & Project Setup | Prepare methylene blue stock solution for the dye-removal groups | Weigh and dilute per 'Supplies & Orders' Part C. | — | Medium | Not started | 2026-09-30 |  |  |  | Suggested (verify)
T22 | 5. Lab & Project Setup | Get the SDS sheets and set up labeled waste containers | Download the Safety Data Sheets for Na₂S₂O₄ (Sigma 157953) and methylene blue (Sigma 66720) and keep them in the lab. Ask the lab / EHS how dye and sulfite-containing waste must be collected. | Lab personnel / stockroom | Medium | Not started | 2026-09-30 |  |  |  | Suggested (verify)
T23 | 6. Academic & Assessment | Ask Luis about the quiz | Grading criteria / rubric for Quiz 1 and how to handle the two students with no scores. | Luis | High | Done | 2026-09-23 |  |  |  | Meeting w/ Dr. Gomez
T24 | 6. Academic & Assessment | Ask Luva to talk with Luis | From the meeting notes. | Luva | Medium | Done | 2026-09-23 |  |  |  | Meeting w/ Dr. Gomez
T25 | 6. Academic & Assessment | Finish grading Quiz 1 per the instructor's criteria | 50 of 52 students graded. Missing: Gavin Cappel, Michelle Gutierrez. See Student_Roster_and_Quiz1_Grades.xlsx. | Luis | High | Done | 2026-09-25 |  |  |  | Previous TA list
T26 | 6. Academic & Assessment | Support administration & supervision of quizzes and assessments | As assigned by the instructors. | Dr. Gomez | Medium | Ongoing |  |  |  |  | Previous TA list
T27 | 6. Academic & Assessment | Support students during projects | Clarify procedures and questions within the scope of the TA role. | — | Medium | Ongoing |  |  |  |  | Previous TA list
T28 | 6. Academic & Assessment | Keep instructors updated on progress, difficulties and team needs | Short weekly update (this Dashboard can help). | Dr. Gomez | Medium | Ongoing |  |  |  |  | Previous TA list
T29 | 7. Student Project Guidance | Ask each group for design alternatives with pros and cons | Advantages / disadvantages of the different design alternatives. | Student groups | Medium | Not started | 2026-10-01 |  |  |  | Meeting w/ Dr. Gomez
T30 | 7. Student Project Guidance | Ask each group for a simple sketch of their idea | A simple sketch of what they are thinking about. | Student groups | Medium | Not started | 2026-10-01 |  |  |  | Meeting w/ Dr. Gomez
T31 | 7. Student Project Guidance | Ask each group for background and an introduction to the problem | Give meaning to the problem: why dye removal / oxygenation matters. | Student groups | Medium | Not started | 2026-10-01 |  |  |  | Meeting w/ Dr. Gomez
↓ Add new tasks here: type an ID (e.g., T32) in column A, then fill the row — it is counted on the Dashboard automatically.
Formulas:
Days Left = IF(OR([ID]="",[Status]="Done",[Status]="Ongoing",[Target Date]=""),"",[Target Date]-TODAY())
Flag = IF([ID]="","",IF([Status]="Done","Done",IF([Status]="Ongoing","Ongoing",IF([Target Date]="","No date",IF([Target Date]<TODAY(),"Overdue",IF([Target Date]-TODAY()<=3,"Due soon","On track"))))))

## Supplies & Orders
Supplies & Orders + Na₂S₂O₄ Dose Calculator
Part A: what to get (check the lab stockroom first). Part B: sodium dithionite needed to deoxygenate 1 L of water, scaled to the class. Part C: methylene blue stock for the dye-removal half. Blue cells = inputs.
PART A — Shopping list
# | Item | Used for | Vendor | Catalog # | Pack size | Qty | Unit Price (USD) | Subtotal (USD) | Link | Priority | Status | Notes
1 | Sodium dithionite, Purified (Reagents brand), wide-mouth amber glass bottle | Oxygenation — removes dissolved O₂ | Cole-Parmer | UX-78919-04 (Mfr C2316300-500C2) | 500 g | 1 | 68.6 |  | Cole-Parmer page | Must have | To order | Chosen vendor. Purity not stated on the page ("Purified") — enter the assay from the Certificate of Analysis in Part B step 9 (currently 82.5%, the Sigma 157953 value). Class needs only ~0.65 g per run; keep the bottle tightly closed and dry and date it when opened. Normally hazmat (UN1384, class 4.2) — confirm shipping cost at checkout. Cheaper alternative: Sigma 157953-5G, 5 g, $46.70.
2 | Methylene Blue hydrate (Sigma M4159) | Dye-removal half (+ optional O₂ color indicator) | Sigma-Aldrich | M4159-25G | 25 g | 1 | 53.97 |  | Sigma-Aldrich B2B page | Must have | To order | Chosen product (TTU B2B price). Check the dye content on the lot Certificate of Analysis and enter it in Part C step 7 (currently 97%, the value for 66720). 25 g is far more than needed (~0.26 g per 1 g/L stock batch).
3 | 1000 mL wide-mouth PP bottle with leak-proof screw cap (United Scientific 33310) | Oxygenation test vessel (1 L) | Amazon | B07DHWGFJM | 1 bottle | 12 | 5.99 |  | Amazon (previous TA's example) | Must have | To order | Default = the previous TA's example: true 1000 mL, 63-415 cap with seal ring, cap can be drilled for a port. Translucent → a color indicator is harder to see; if you use one, switch to item 4 (Qty here 0, Qty there 1, Part B volume 0.9 L). Qty: meeting said 11 (likely one per group for the whole class: 52 ÷ 5 → 11); previous TA planned 12 (11 + 1 spare). Same spec: US Plastic #76632, 6-pack $33.10.
4 | ALTERNATIVE: 32 oz clear PET jars with screw lids, 12-pack (OMNISAFE) | Oxygenation vessel — cheaper & clear | Amazon | B0CLXQCS45 | 12 jars + lids | 0 | 28.99 |  | Amazon | Optional |  | Choose EITHER this OR the PP bottles. Clear walls (best for a color indicator) and PET is a better O₂ barrier — but 32 oz = 946 mL, so use ~0.9 L per jar (change 'Water volume per container' in Part B). 'Airtight' is a vendor claim — test one jar first.
5 | Replacement membrane cap for the damaged DO probe (Vernier MEM — if the probe is a Vernier DO-BTA) | Repair the existing DO probe (cheapest fix) | Vernier | MEM | 1 cap | 1 | 19 |  | Vernier | Depends on DO method | Check lab first | Check brand/model of the broken probe first. If only the membrane/electrolyte failed, a new cap + filling solution may fix it. Clark-type probes consume O₂ and need stirring.
6 | Optical dissolved-oxygen probe (Vernier Go Direct GDX-ODO) | Quantitative DO in the sealed container | Vernier | GDX-ODO | 1 probe | 1 | 409 |  | Vernier | Depends on DO method | Check lab first | Department/TA purchase, not a group budget item. 90% reading in 40 s, factory calibrated, no stirring, does not consume O₂. Seal it through the lid with a stopper/grommet. 1–2 probes shared across groups.
7 | Dissolved-oxygen colorimetric kit 1–12 ppm (CHEMetrics CHEMets K-7512) | Spot-check DO (start / end) | CHEMetrics (via MegaDepot) | K-7512 | 30 tests | 1 | 69.99 |  | CHEMetrics | Depends on DO method | Check lab first | ~2 min per test, no instrument. Must draw a ~25 mL sample (opens the closed system); ±1 ppm resolution; leftover dithionite biases low.
8 | Dissolved-oxygen colorimetric kit 0–1 ppm (CHEMetrics CHEMets K-7501) | Confirm water is near 0 ppm after dithionite | CHEMetrics (via MegaDepot) | K-7501 | 30 tests | 1 | 70.3 |  | CHEMetrics | Depends on DO method | Check lab first | Checks that deoxygenation worked (0–1 ppm). Sampling must avoid air contact (syringe through a septum).
9 | Resazurin sodium salt (optional O₂ indicator, pink ↔ colorless) | Oxygenation — alternative color indicator | Sigma-Aldrich | R7017-1G | 1 g | 1 | 44.1 |  | Sigma-Aldrich page | Optional | Check lab first | Only if you prefer a pink indicator (avoids confusion with the methylene-blue half). Qualitative only — shows O₂ ingress, not mg/L.
10 | Self-sealing butyl injection ports, 7 mm (1/4 in) hole | Sampling port through the lid | Amazon | B08XJJ4VV3 | 100 ports | 1 | 6.49 |  | Amazon | Depends on DO method | Check lab first | Only if samples are drawn through the lid. Solid rubber needs a sharp needle (blunt tips core the rubber) — for needle-free sampling use a Luer-lock stopcock/bulkhead instead. Seal with silicone if the cap is thick.
11 | Disposable 10 mL Luer-lock syringes, no needle | Sampling / dosing | Amazon | B0DXMYP29M | 100 syringes | 1 | 17.99 |  | Amazon | Optional | Check lab first | Most teaching labs already have these.
12 | Plastic transfer pipettes, 3 mL graduated | Adding dye / indicator | Amazon | B00WLIQHQ0 | 100 pipettes | 1 | 6.19 |  | Amazon | Optional | Check lab first | Almost always in stock in the lab.
13 | Weighing boats (7 mL + 100 mL set) | Weighing Na₂S₂O₄ and methylene blue | Amazon | see link | 100 boats | 1 | 11.99 |  | Amazon | Must have | To order | Link provided by the TA (Sep 28, 2026). Unit price is still the $11.99 from the earlier listing (B089LL2XHR) — update column H and pack size if the new listing differs.
14 | Parafilm M, 2 in × 250 ft | Extra seal on lids / ports | Amazon | PM992 (672050) | 1 roll | 1 | 30.96 |  | Amazon | Optional | Check lab first | Priciest small item — the lab very likely has it.
15 | Plastic cuvettes, polystyrene, 4.5 mL (340–750 nm) | Dye-removal half — absorbance at 664 nm | Amazon | Globe 111137 | 100 cuvettes | 1 | 23.56 |  | Amazon | Optional | Check lab first | Only if students measure methylene blue with a spectrophotometer that takes 12.5 mm square cuvettes.
16 | Lab labeling tape, 1 in | Label vessels by group / time | Amazon | B08MLGSCVD | 1 roll | 1 | 9.49 |  | Amazon | Optional | Check lab first | Masking tape + marker works too.
17 | Lab coats | Safety — all students | Lab (Mike Nichols) | — | — |  |  |  |  | Must have | Available in lab | Already available (previous TA). Verify sizes/quantity for ~52 students.
18 | Nitrile gloves | Safety — all students | Lab (Mike Nichols) | — | — |  |  |  |  | Must have | Available in lab | Already available (previous TA).
19 | Safety glasses | Safety — all students | Lab (Mike Nichols) | — | — |  |  |  |  | Must have | Available in lab | Pending a support/rack for storage — follow up with Mike Nichols (task T05).
20 | Balance (0.001 g), spatulas, 1 L volumetric flask / graduated cylinder, DI or tap water | Weighing & preparing solutions | Lab | — | — |  |  |  |  | Must have | Available in lab | Needed to weigh ~0.07 g Na₂S₂O₄ per liter — an analytical balance (0.001 g or better) is best.
21 | PTFE magnetic stir bar set, assorted (include 25–35 mm bars for 1 L) | Mixing the 1 L bottles | Amazon |  | set | 1 |  |  | Amazon | Must have | To order | Link provided by the TA. Price not entered yet — type it in column H (estimate ~$10–15). Check the lab stir plates first; bars must be long enough to mix 1 L.
22 | Disposable plastic lab spatulas (PP) | Weighing Na₂S₂O₄ and methylene blue | Amazon |  | see link | 1 |  |  | Amazon | Must have | Check lab first | Link provided by the TA. Price not entered yet — type it in column H. Row 20 lists spatulas as available in the lab; buy only if plastic ones are needed. Likely does not fit the $200 budget.
23 | [11 empty] | ↑ Spare rows — type new items here; they are already included in the totals.
|  |  | Must-have items to buy (est.) | [6 empty] | Items by status
|  |  | Optional + DO-method items (if all were bought) | [6 empty] | Check lab first
|  |  | Everything listed (upper bound) | [6 empty] | Available in lab
|  |  | Budget available (ask Dr. Gomez — FOP) |  |  |  |  | 200 |  | To order
|  |  | Remaining after all items | [6 empty] | Ordered
|  |  | Sigma-Aldrich items still without a price | [6 empty] | Received
Prices checked on vendor pages Sep 22, 2026 (hover over a price for its source). Sigma-Aldrich shows TTU prices after login — type them in column H and all totals update. | [9 empty] | Not needed
PART B — Sodium dithionite (Na₂S₂O₄) needed to remove dissolved oxygen from 1 L of water, scaled to the class
Na₂S₂O₄ reacts with dissolved oxygen 1:1 (Na₂S₂O₄ + O₂ + H₂O → NaHSO₄ + NaHSO₃). The calculator finds how much O₂ is dissolved in the water at the lab's temperature and elevation, converts it to grams of Na₂S₂O₄, corrects for purity and adds an excess (row V shows how much O₂ that excess will absorb). Change only the blue cells; the green cells are the answer. Pilot-test once before class.
Step | Quantity |  |  |  | Value | Unit | How it's calculated / source
Inputs — class size & setup (edit the blue cells)
1 | Students doing the oxygenation project |  |  |  | 25 | students | From your request: ~25 students (about half the class). The roster has 52 → 26 per half = 6 groups of 5 — change this if needed.
2 | Students per group |  |  |  | 5 | students/group | Meeting notes: 4 to 5 students per group.
3 | Containers (runs) per group |  |  |  | 1 | containers | 1 = each group runs one 1-L container. Increase for replicates/controls.
4 | Water volume per container |  |  |  | 1 | L | Target solution volume = 1 L per container.
5 | Extra liters for TA pilot tests |  |  |  | 2 | L | Trial runs before class (recommended).
6 | Safety margin on total volume |  |  |  | 20% | % | Covers spills / repeats.
Inputs — water & chemical conditions
7 | Water temperature |  |  |  | 22 | °C | Room-temperature tap/DI water. DO saturation depends on temperature.
8 | Elevation of the lab |  |  |  | 976 | m | Lubbock / Texas Tech ≈ 976 m (3,202 ft), from TTU's Lubbock geography page. Higher elevation → less O₂ in the water.
9 | Purity (assay) of the Na₂S₂O₄ you buy |  |  |  | 82.5% | fraction | Currently the Sigma 157953 value (≥82.5%). The Cole-Parmer 'Purified' product does not state a percentage — enter the assay from its Certificate of Analysis.
10 | Excess factor over stoichiometric dose |  |  |  | 1.5 | × | 1.5× covers the measured ratio (1.2 ± 0.2 mol/mol at 25 °C) and losses while weighing. Keep it 1.25–1.5×: leftover dithionite keeps eating the O₂ that diffuses back in and delays the re-oxygenation you want to measure.
11 | Methylene blue added as O₂ color indicator (0 if none) |  |  |  | 0 | mg/L | Enter 2–5 mg/L if methylene blue is also used as the O₂ color indicator (it turns colorless when reduced, blue again with O₂). Adds ~0.54 mg Na₂S₂O₄ per mg MB.
Constants (from the literature — do not change)
| Molar mass Na₂S₂O₄ |  |  |  | 174.11 | g/mol | Anhydrous sodium dithionite.
| Molar mass O₂ |  |  |  | 31.998 | g/mol
| Molar mass methylene blue (chloride, anhydrous) |  |  |  | 319.85 | g/mol | C₁₆H₁₈ClN₃S.
| mol Na₂S₂O₄ per mol O₂ |  |  |  | 1 | mol/mol | Na₂S₂O₄ + O₂ + H₂O → NaHSO₄ + NaHSO₃ (1:1). Measured 1.2 ± 0.2 at 25 °C (Tao et al., J. Phys. Chem. A 2008) — covered by the excess factor. Enter 2 only for a worst-case check (then lower the excess).
| mol Na₂S₂O₄ per mol methylene blue |  |  |  | 1 | mol/mol | MB⁺ + 2e⁻ → leuco-MB (colorless); S₂O₄²⁻ supplies 2 e⁻ → 1:1.
Step-by-step calculation
A | Number of groups |  |  |  |  | groups | → ROUNDUP(students ÷ students per group)
B | Total volume of deoxygenated water to prepare |  |  |  |  | L | → (groups × containers × volume + pilot) × (1 + margin)
C | Water temperature in kelvin |  |  |  |  | K | → °C + 273.15
D | O₂ saturation at sea level (fresh water, 1 atm) |  |  |  |  | mg/L | Benson & Krause (1984) equation, APHA Standard Methods 4500-O.
E | Barometric pressure at the lab |  |  |  |  | atm | Standard atmosphere: P = (1 − 2.25577×10⁻⁵ × h)^5.25588
F | Water-vapor pressure at this temperature |  |  |  |  | atm | Standard Methods 4500-O: ln Pwv = 11.8571 − 3840.70/T − 216961/T²
G | θ (Standard Methods pressure-correction term) | [5 empty] | θ = 0.000975 − 1.426×10⁻⁵ t + 6.436×10⁻⁸ t²
H | O₂ dissolved in the water at the lab (saturation) |  |  |  |  | mg/L | Pressure-corrected: C = C* · P · [(1 − Pwv/P)(1 − θP)] / [(1 − Pwv)(1 − θ)]
I | O₂ to remove per liter |  |  |  |  | mmol/L | → mg/L ÷ 32.00 mg/mmol
J | Methylene blue to reduce per liter |  |  |  |  | mmol/L | → MB mg/L ÷ 319.85 mg/mmol (0 if no indicator)
K | Na₂S₂O₄ needed (stoichiometric) |  |  |  |  | mmol/L | → O₂ mmol × 1 + MB mmol × 1
L | Mass of pure Na₂S₂O₄ (stoichiometric) |  |  |  |  | mg/L | → mmol × 174.11 mg/mmol
M | Mass of the product you buy (purity-corrected) |  |  |  |  | mg/L | → pure mass ÷ purity
N | DOSE for 1 L of water (with excess factor) |  |  |  |  | mg per 1 L | → purity-corrected mass × excess factor
O | DOSE for 1 L of water |  |  |  |  | g per 1 L | Dose per liter of water. The amount to weigh into each container is row P.
P | Per container |  |  |  |  | g/container | → g/L × volume per container
Q | Per group |  |  |  |  | g/group | → g/container × containers per group
R | TOTAL Na₂S₂O₄ for the whole class |  |  |  |  | g | → g/L × total volume (incl. pilot + margin)
S | Bottle size you plan to buy |  |  |  | 500 | g | Match to the pack in Part A (Cole-Parmer 500 g). Keep it tightly closed and dry; write the opening date on the bottle.
T | Bottles needed |  |  |  |  | bottles | → ROUNDUP(total g ÷ bottle size)
U | Liters one bottle can deoxygenate |  |  |  |  | L | → bottle g ÷ dose g/L — shows how much spare you have.
V | O₂ the leftover (excess) Na₂S₂O₄ will absorb before DO starts rising |  |  |  |  | mg/L | → excess product × purity ÷ 174.11 ÷ (mol/mol) × 32.00. Compare with row H: re-oxygenation only shows after this much O₂ has diffused in — measure the lag in the pilot test.
Safety & handling notes (sodium dithionite)
• Hazards: self-heating solid, may catch fire (H251); harmful if swallowed (H302); listings also show eye irritation (H319) and/or toxic to aquatic life (H411); contact with ACIDS releases toxic SO₂ gas. Download the SDS for 157953 from the Sigma page and keep it in the lab. Store away from acids.
• Store tightly closed, cool and DRY — never let water into the bottle; it slowly degrades once opened, so write the opening date on it. Shipped as hazmat (UN1384, class 4.2): expect extra shipping fees / lead time.
• Weigh it right before use and add it directly to the water (or make a small concentrated solution in a closed vial and use it immediately) — dissolved dithionite decomposes within hours in air.
• Do not overdose: extra dithionite consumes the incoming O₂ and delays re-oxygenation. Give every group the same dose and start the clock only when the DO starts to rise.
• The products (bisulfate/bisulfite) are acidic — in unbuffered DI water the pH can drop to ~3.6 (estimate), which also speeds decomposition. Tap water or a light buffer avoids this.
• Fill containers to the brim or record the headspace: 100 mL of air holds ~24 mg of O₂ — about 3× the O₂ dissolved in 1 L of water — so headspace dominates the result.
• Wear nitrile gloves and safety glasses. Sweep spills up dry (do not wash with water). Collect dithionite and methylene-blue waste — do not pour down the drain (ask the lab / EHS).
Check: DO-saturation formula vs. published table (sea level, fresh water)
| Temperature |  |  |  | Formula (mg/L) | Table (mg/L) | Difference (mg/L)
| 15 |  |  |  |  | 10.08
| 18 |  |  |  |  | 9.47
| 20 |  |  |  |  | 9.09
| 22 |  |  |  |  | 8.74
| 25 |  |  |  |  | 8.26
| 28 |  |  |  |  | 7.83
| 30 |  |  |  |  | 7.56
Table values: USGS (2020) Techniques & Methods 9-A6.2, Table 6.2-2 at 760 mmHg (same values as USGS DOTABLES). Equation: USGS Tech. Memo 2011.03 (Benson & Krause).
PART C — Methylene blue solution for the dye-removal half of the class
Step | Quantity |  |  |  | Value | Unit | How it's calculated / source
Inputs (edit the blue cells)
1 | Students doing methylene-blue removal |  |  |  | 25 | students | The other half of the class.
2 | Students per group |  |  |  |  | students/group | Linked to Part B (same group size).
3 | Dye solution per group |  |  |  | 2 | L | Dye water each group needs to test its treatment design (e.g., 2 runs × 1 L). Adjust once the procedure is set.
4 | Target methylene blue concentration |  |  |  | 10 | mg/L | Typical student adsorption labs use 10–50 mg/L. For absorbance at 664 nm, dilute samples below ~4–5 mg/L and build a calibration curve (0.5–5 mg/L).
5 | Stock solution concentration |  |  |  | 1000 | mg/L | 1 g/L stock is easy to weigh and dilute.
6 | Stock volume to prepare (volumetric flask) |  |  |  | 250 | mL | Use a volumetric flask of this size.
7 | Dye content of the methylene blue you buy |  |  |  | 97% | fraction | Currently the value for Sigma 66720 (≥97.0%). You are buying M4159 — enter the dye content from its lot Certificate of Analysis and confirm with a calibration curve at 664 nm.
8 | Safety margin |  |  |  |  | % | Linked to Part B.
Calculation
A | Number of groups |  |  |  |  | groups | → ROUNDUP(students ÷ students per group)
B | Total dye solution to prepare |  |  |  |  | L | → groups × L per group × (1 + margin)
C | Methylene blue powder to weigh for the stock |  |  |  |  | mg | → stock mg/L × flask mL ÷ 1000 ÷ dye content
D | Stock to add per 1 L of working solution |  |  |  |  | mL per 1 L | → target ÷ stock × 1000 mL (then fill to 1 L with water)
E | Stock needed for the whole class |  |  |  |  | mL | → mL per L × total liters
F | Stock batches (flasks) needed |  |  |  |  | batches | → ROUNDUP(stock needed ÷ flask volume)
G | Total powder to weigh (all stock batches) |  |  |  |  | mg | → powder per flask × number of batches
H | Dye that ends up in the working solutions (info only) |  |  |  |  | mg | → target mg/L × total L ÷ dye content
Note on H6: Cole-Parmer list price $68.60, ships by Oct 05 (from product page screenshot provided by the TA, Sep 28, 2026).
Note on H7: TTU B2B (punchout) price $53.97 for 25 g, provided by the TA, Sep 28, 2026.
Note on H8: Amazon, sold by Amazon.com, $5.99 each, in stock (checked Sep 22, 2026). This is the previous TA's example link (a.co/d/0c6b1Ve2).
Note on H9: Amazon, $28.99 per 12-pack, in stock (checked Sep 22, 2026). Qty set to 0 — change to 1 if you choose this instead of the PP bottles.
Note on H10: vernier.com, $19.00 (checked Sep 22, 2026). Use the equivalent part if the probe is another brand.
Note on H11: vernier.com, $409.00 (checked Sep 22, 2026). PASCO PS-3246 is similar (~$404 incl. tariff surcharge).
Note on H12: MegaDepot $69.99 (checked Sep 22, 2026); Cole-Parmer ~$90.20.
Note on H13: MegaDepot $70.30 sale / $76.44 list (checked Sep 22, 2026).
Note on H14: Sigma-Aldrich US list price, 1 g = $44.10, checked Sep 22, 2026.
Note on H15: Amazon $6.49 (checked Sep 22, 2026).
Note on H16: Amazon $17.99 (checked Sep 22, 2026). Smaller: 20 × 20 mL for $12.99 (B0F98KGPZ3).
Note on H17: Amazon $6.19 (checked Sep 22, 2026).
Note on H18: Amazon $11.99 (checked Sep 22, 2026).
Note on H19: Amazon $30.96 (checked Sep 22, 2026).
Note on H20: Amazon $23.56 (checked Sep 22, 2026).
Note on H21: Amazon $9.49 (checked Sep 22, 2026).
Note on I33: Budget $200, provided by the TA, Sep 28, 2026.

## DO Methods
Dissolved-Oxygen Measurement — Options & Decision Matrix
The lab's DO probe is damaged. These are INITIAL alternatives (not a final choice). Scores 1–5 (5 = best) are editable starting suggestions; change the weights to match what matters most. Availability = can be had quickly (in lab or off-the-shelf in the US). The weighted score and rank update automatically.
Criteria weights → | [9 empty] | 20% | 20% | 15% | 15% | 10% | 10% | 10%
# | Method | How it works | Measurement time | Closed system? | Open / penetrate container? | Accuracy / range | Equipment & cost (approx.) | Example product / link | Pros / Cons | Measure time (~2 min) | Closed system | No opening / penetration | Accuracy | Ease of use | Availability (in lab / off- the-shelf) | Cost | Weighted score | Rank | Decision | Gives mg/L?
1 | Optical sensor spots + fiber reader (PreSens SP-PSt3 + Fibox 4, or PyroScience OXSP5 + FireSting-O2) | A luminescent spot glued inside the clear wall is quenched by O₂; a fiber-optic reader outside the wall reads DO through the wall. | Seconds per reading; logs continuously | Yes — fully closed | None after the spot is glued in once (needs a clear wall) | Research grade after 2-point calibration; down to near-zero O₂ | Spots ~$40 each (PyroScience €300/8); reader quote-only, est. $2,000–5,000 | PyroScience OXSP5 spots | PROS: Truly non-invasive; continuous DO-vs-time curves; very accurate; consumes no O₂. CONS: Reader costs thousands (quote-only, imported). Worth it only if someone at TTU already owns a reader — then buy spots only. | 5 | 5 | 5 | 5 | 3 | 2 | 1 |  |  | Evaluate | Y
2 | Optical DO probe sealed through the lid (Vernier GDX-ODO; PASCO PS-3246 similar) | Luminescent cap on the probe tip; reports mg/L with automatic temperature/pressure compensation. | 90% of reading in 40 s | Yes, if sealed through the lid with a stopper/grommet | One-time sealed hole in the lid | 0–20 mg/L, ±0.2 mg/L (<10 mg/L) | $409 per probe (Vernier); PASCO ~$404. Replacement sensing cap $89 (2-yr warranty). ~$0 per test | Vernier GDX-ODO | PROS: Direct replacement for the broken probe; factory calibrated; no stirring; consumes no O₂; easy for undergrads. (Closed-system scores assume the probe stays sealed in the lid for a whole run — lower them if 1–2 probes are moved between containers.) CONS: $409 each — share 1–2 probes across groups; probe must be sealed through the lid; removing it lets air in. | 5 | 4 | 4 | 4 | 5 | 5 | 2 |  |  | Shortlist | Y
3 | Repair the existing DO probe (new membrane cap + filling solution) | Most 'damaged' Clark/polarographic probes fail at the membrane or electrolyte; replacing them can restore the probe. | 30–45 s per reading (+ ~10 min warm-up) | Yes, if sealed through the lid (needs stirring) | One-time sealed hole in the lid | e.g., Vernier DO-BTA 0–15 mg/L, ±0.2 mg/L | Membrane cap $19 (Vernier MEM) + filling solution ≈ $20–50 total | Vernier MEM membrane cap | PROS: Cheapest route to a quantitative probe; uses equipment the lab already owns. CONS: Works only if the damage is the membrane/electrolyte. Consumes O₂ and needs stirring in a small sealed vessel. | 3 | 4 | 4 | 4 | 3 | 4 | 5 |  |  | Shortlist | Y
4 | Methylene blue / leuco-methylene blue color indicator (with Na₂S₂O₄) | Dithionite turns methylene blue colorless; O₂ entering the sealed container turns it blue again. | Instant (visual) or 10–30 s phone photo | Yes — read through a clear wall | None | Qualitative / semi-quantitative: shows O₂ ingress (time to turn blue), not mg/L. Saturates at ~0.1–0.25 mg/L O₂ for 2–5 mg/L dye | Chemicals already being bought; < $0.10 per test | Sigma-Aldrich 66720 methylene blue | PROS: Almost free; every group can run it; makes O₂ diffusion visible; phone-camera RGB analysis is a nice design add-on. CONS: Not a DO concentration; light-sensitive; depends on dye/reductant dose — cross-check with a probe or CHEMets. | 5 | 5 | 5 | 2 | 5 | 5 | 5 |  |  | Shortlist | N
5 | Resazurin / resorufin color indicator | Reduced (colorless) dihydroresorufin turns pink when O₂ returns. | Instant (visual) | Yes — read through a clear wall | None | Qualitative only; responds to trace O₂ earlier than methylene blue | Small bottle of resazurin; < $0.10 per test | Sigma-Aldrich R7017 resazurin | PROS: Very cheap; closed system; pink color avoids confusion with the methylene-blue half. CONS: No DO calibration; first reduction step is irreversible; one more chemical to buy. | 5 | 5 | 5 | 1 | 4 | 4 | 5 |  |  | Evaluate | N
6 | Colorimetric ampoules (CHEMetrics CHEMets K-7512 1–12 ppm / K-7501 0–1 ppm) | A vacuum ampoule snapped in a sample fills itself; DO develops a color matched to a comparator. | ~2 min + ~1 min sampling | No — a ~25 mL sample must leave the container | Open the lid or syringe through a septum | K-7512: ±~1 ppm steps; K-7501: 0–1 ppm (MDL 0.025 ppm) | ~$70 per kit of 30 tests (~$2.3/test); no instrument | CHEMetrics K-7512 | PROS: Cheap, fast, foolproof; K-7501 confirms the water really is near 0 ppm. CONS: Destructive — breaks the closed system; coarse resolution; leftover dithionite biases low. | 4 | 2 | 2 | 2 | 5 | 5 | 4 |  |  | Evaluate | Y
7 | Winkler (iodometric) titration kit (LaMotte 5860-01 or Hach OX-2P) | O₂ is fixed as manganese oxide, then titrated with thiosulfate to a starch endpoint. | 10–15 min per sample | No | Must open the container and fill a sample bottle | Reference method; LaMotte 0–10 ppm in 0.2 ppm steps; Hach OX-2P 0.2–4 & 1–20 mg/L | Kit: LaMotte 5860-01 ~$63–104 / 50 tests; Hach OX-2P ~$189 / 100 (search-listing prices). DIY Sigma reagents ≈ $407 (sodium azide is fatal on skin contact) | LaMotte 5860-01 | PROS: Classical standard method with high teaching value; no instrument. CONS: Slowest (far from ~2 min); destructive; dithionite/sulfite interfere (low bias); several hazardous reagents. | 2 | 1 | 1 | 4 | 2 | 5 | 4 |  |  | Rejected | Y
8 | Hach AccuVac ampoules + DR300 pocket colorimeter | Evacuated ampoule filled under the sample; colorimeter reads the color at 520 nm. | ~4–5 min | No — sample removed | Open the container (≥40 mL sample) | 0.3–15 mg/L, digital readout | Ampoules ~$55 / 25; DR300 ~$711 (search-listing prices) | Hach 2515025 AccuVac | PROS: Numeric reading; could use an existing spectrophotometer (18 mm vials). CONS: Destructive and slow; colorimeter costs more than an optical probe. | 3 | 2 | 2 | 4 | 4 | 4 | 2 |  |  | Evaluate | Y
9 | Arduino galvanic DO kit (DFRobot SEN0237-A; Atlas Scientific kit similar) | Galvanic (Clark-type) cell behind a membrane; current ∝ O₂, read by an Arduino. | 98% response in ~90 s | Yes, if sealed through the lid (needs stirring) | One-time sealed hole in the lid | 0–20 mg/L; accuracy not specified (≈ ±0.5 mg/L est.) | $169 kit + Arduino (~$190–200); Atlas kit $355 | DFRobot SEN0237-A | PROS: Cheapest continuous electronic option; fits an engineering-design build. CONS: Consumes O₂ and needs stirring; membrane/electrolyte upkeep; Arduino setup takes TA time. | 4 | 4 | 4 | 3 | 2 | 4 | 3 |  |  | Evaluate | Y
10
11 | ↑ spare rows: add another technique and score it
Recommendation (research summary): (1) This week: find the brand/model of the broken probe — if it is a membrane-type probe, try a new membrane cap (~$19) first. (2) Main quantitative method: 1–2 optical DO probes (Vernier GDX-ODO, $409) sealed through the lid — fast, no stirring, consumes no O₂. (3) Every group, nearly free: methylene blue (or resazurin) color indicator in a clear container, photographed at fixed times — shows O₂ INGRESS, not mg/L. (4) Optional cross-check: CHEMets K-7501 (0–1 ppm) to confirm the water starts near 0, K-7512 for the end point. Not recommended as the main method: Winkler (slow, destructive, dithionite interferes) and optical spots (reader costs thousands unless borrowed).
Previous TA's note: these are starting alternatives. If another technique fits the project's needs and constraints better, use a spare row and score it the same way. 'Gives mg/L?' separates true DO measurements from color indicators on the Dashboard.

## Contacts
Contacts — Who To Ask For What
Open tasks are counted automatically from the Task Tracker (Who / Contact column contains the search key). Next step = that person's open task with the earliest target date.
Name | Role | What to ask / coordinate | Email / phone | Open tasks | Next step (earliest due) | Search key
Dr. Gomez | Course professor | FOP account for purchases · budget ('under $80' — per group? confirm) and what is due Oct 1 · project split (methylene blue vs. oxygenation) · group formation · choice of DO method |  |  |  | Gomez
Mike Nichols | Lab / safety equipment coordinator | Lab coats, gloves, safety glasses + rack · lab keys and access · lab-specific training · lab prep |  |  |  | Nichols
Luis | Instructor / grading contact (confirm role) | Quiz 1 grading criteria · missing quiz scores (2 students) |  |  |  | Luis
Luva | Contact who will talk with Luis (confirm role) | Follow-up with Luis (from the meeting notes) |  |  |  | Luva
Lab personnel / stockroom | Chemical inventory | Is Na₂S₂O₄ (sodium hydrosulfite) in stock? Methylene blue? Balances, volumetric flasks, DI water · waste disposal rules |  |  |  | Lab personnel
TTU EHS | Environmental Health & Safety | Required lab safety training · chemical safety (SDS for Na₂S₂O₄ and methylene blue) · waste pickup |  |  |  | EHS
Note on G4: Word searched for in the Task Tracker 'Who / Contact' column. To add a person, fill a new row here (name + search key) and copy the Open tasks / Next step formulas down.

## Meeting Notes
Meeting Notes Log
One row per meeting. Link action items to Task IDs so they show up in the Task Tracker.
Date | Meeting with | Key points | Action items | Task IDs
| Dr. Gomez (professor) | • Class project: half on METHYLENE BLUE REMOVAL, half on OXYGENATION. • October 1 — under $80 per group (4 to 5 students per group). • Ask Dr. Gomez for the FOP (purchasing account). • Buy ~11 plastic containers with lids (1000 mL or 500 mL, cheap). • Buy methylene blue dye. • Need water with no dissolved oxygen → use a salt that consumes O₂: Na₂S₂O₄ (sodium dithionite). • Find a way to measure DO in the solution — maybe something that changes color with O₂ level. • Ask Luva to talk with Luis; ask Luis about the quiz. • Students: design alternatives with pros & cons; a simple sketch; background and introduction; give meaning to the problem. | Get FOP → order Na₂S₂O₄, methylene blue, containers (T07, T09, T10, T12) Choose DO measurement method (T14–T16) Talk to Luva / Luis about the quiz (T23, T24) Tell students what to include: alternatives, sketch, background (T29–T31) | T07, T09–T16, T20, T23, T24, T29–T31
| Previous TA (hand-off document) | • Training: lab safety courses + FERPA (needed for Canvas). • Safety equipment with Mike Nichols: coats & gloves available; safety glasses waiting for a rack. • Keys / lab access from Mike Nichols. • Chemicals: confirm sodium dithionite with lab personnel. • DO probe is damaged → compare optical sensor spots, colorimetric methods, Winkler titration (time ~2 min, closed system, penetration, accuracy, ease, availability, cost). • ~1 L plastic containers with lids, plan to buy 12. Example: https://a.co/d/0c6b1Ve2 • Disassemble old water-treatment prototypes. • Quizzes: support, grade, communicate with instructors. | All captured in the Task Tracker (Source = 'Previous TA list'). | T01–T06, T08, T11, T14, T15, T18, T19, T25–T28
Note on A5: Enter the date of the meeting with the professor.